## Sheet1
Tasks to do | Due Dates | Assignee | Notes | Completed
Complete Updating the SPMP | 2020-11-18 | Adebayo/Neal | We are close to completing it | TRUE
Complete all the group project Deliverables | 2020-11-18 | Adebayo/Neal | As of now we only have to update the SPMP to complte it | TRUE
Need to finish the front end portion of the group project. | 2020-12-01 | Sudeep/Aayush | Pending front end portion | FALSE
Try completing the back end portion of the froup project. | 2020-12-01 | Neal/Adebayo | Pending back end portion. | FALSE
Complete adding the donation part in the same domain of the project. | 2020-12-01 | Adebayo | Pending this portion as well. | FALSE
Test Site | 12/2/20 - 12/5/20 | Neal/Adebayo/Sudeep/Aayush | We are close to completing the website to test it. | FALSE
Deploy Site | 2020-12-07 | Neal/Adebayo/Sudeep/Aayush |  | FALSE
Finalize the Reports | 2020-12-07 | Neal/Adebayo/Sudeep/Aayush |  | FALSE
Presentation | 2020-12-08 | Neal/Adebayo/Sudeep/Aayush | Presentation is due on 12/8 lets try to finish the website by 12/7. | FALSE
Team-mates Evaluation | 2020-12-08 | Neal/Adebayo/Sudeep/Aayush |  | FALSE